## Sheet1
SRNO | MENU NAME | SUB-MENU | COMMENT | FUNCTIONALITY | RESOURCE | DAYS | STATUS
1 | USER MASTER | USER MASTER |  |  | ANAND | 2 days | PENDING
|  | ROLE MASTER |  |  | ANAND |  | PENDING
|  | MENU MASTER |  |  | ANAND |  | PENDING
PENDING
2 | MASTER | ACCOUNT MASTER |  |  | ANKUSH | 2 days | PENDING
|  | CITY MASTER |  |  | VIVEK | 1 days | PENDING
|  | AREA MASTER |  |  | VIVEK |  | PENDING
|  | ITEM MASTER |  |  | VIVEK |  | PENDING
|  | BANK MASTER |  |  | VIVEK |  | PENDING
|  | TRANSPORT MASTER |  |  | VIVEK |  | PENDING
|  | COMPANY MASTER |  |  |  |  | PENDING
3 | DASHBOARD |  | COMMON PAGES/alignment/css/front/icons |  | VIVEK | 2 days | PENDING
| FOOTER (INCLUDE SHORTKEYS) |  |  |  | VIVEK |  | PENDING
| HEADER |  |  |  | VIVEK |  | PENDING
| NAVIGATION BAR (left) |  |  |  | VIVEK |  | PENDING
| LOGIN PAGE |  |  |  | VIVEK |  | PENDING
| NOT FOUND PAGE |  |  |  | VIVEK |  | PENDING