## Sheet1
SRNO | MENU NAME | SUB-MENU | COMMENT | FUNCTIONALITY | RESOURCE | DAYS | STATUS
1 | USER MASTER | USER MASTER |  |  | Anand | 2 days | Progress
|  | ROLE MASTER |  |  | Anand |  | Progress
|  | MENU MASTER |  |  | Anand |  | Progress
2 | MASTER | ACCOUNT MASTER |  |  | Ankush | 2 days | Progress
|  | CITY MASTER |  |  | Vivek | 1 days | Progress
|  | AREA MASTER |  |  | Vivek |  | Progress
|  | ITEM MASTER |  |  | Vivek |  | Progress
|  | BANK MASTER |  |  | Vivek |  | Progress
|  | TRANSPORT MASTER |  |  | Vivek |  | Progress
|  | GROUP MASTER |  |  | Vivek |  | Pending
|  | COMPANY MASTER |  |  | Vivek |  | Progress
3 | DASHBOARD |  | COMMON PAGES/alignment/css/front/icons |  | Vivek | 2 days | Progress
| FOOTER (INCLUDE SHORTKEYS) |  |  |  | Vivek |  | Progress
| HEADER |  |  |  | Vivek |  | Progress
| NAVIGATION BAR (left) |  |  |  | Vivek |  | Progress
| LOGIN PAGE |  |  |  | Vivek |  | Progress
| NOT FOUND PAGE |  |  |  | Vivek |  | Progress